newsletter

LA CARIBE DEVELOPMENT NEWSLETTER 2                                        September 2008

It has been four busy months since we last communicated with you. Once again we are updating you on the progress of La Caribe.

Out of Court Settlement

As you may be aware, C Max Investments 276 (Proprietary) Limited (“C Max”) is the owner of the land on which La Caribe is being developed. C Max and the Marina Martinique Home Owners Association (“MMHOA”) have been involved in some lengthy court cases concerning the marina in general and which delayed transfers taking place in La Caribe in particular.

In terms of an out of court settlement reached between C Max and the MMHOA on 27 August 2008, the parties have buried the hatchet and the development of Phase 2 will once again commence with a spirit of co-operation between the MMHOA and C Max. This spirit of co-operation can only be good for the whole of the marina but specifically buyers of stands on Phase 2 and for you as buyers in La Caribe. We have enclosed the public announcement put out jointly by the MMHOA and C Max for further clarity.

C Max is committed to complete the development of Phase 2 to a very high standard for the benefit of the Marina Martinique community as a whole, and this commitment has been extended to you as buyers in La Caribe. We are certain that the investment you have made in La Caribe which is situate within the secure life style estate of Marina Martinique will stand you well.

Clearance Certificates

Following on from the out of court settlement, C Max, on the provision of electrical and sewerage engineering certificates is entitled to commence with the transfer of certain units in La Caribe. These certificates have been obtained and it is anticipated that the first 16 units in La Caribe will be transferred shortly. The units to be transferred are: Units 43, 45, 46, 47 and 49 through to 60. We congratulate our first transferees and hope you will enjoy your new apartments.

Status of Construction

Units 31 to 42 being in Block D are 99% ready for transfer. The only thing holding up these transfers is the provision of sufficient parking bays, which are currently being constructed.

Units 13 to 18 being in Block F are 80% complete, and units 19 to 30 being Block E are 75% complete.

Our final Block G, being units 1 to 12 on the water, has been marked out and the foundations should commence in October 2008, with completion scheduled for May 2009.

Status of Electricity

La Caribe is to receive a new electrical mini substation of 630 KVa, which has been ordered and is expected to be commissioned towards the end of October 2008.  In the interim, a temporary mini sub station is to be installed which will provide sufficient electricity for the first transfers.

Body Corporate and Sectional Title Register

In terms of the Sectional Title Act, a Body Corporate must be formed when the first transfers take place, and within sixty days of the first transfers taking place, the developer must hold the first general meeting of the Body Corporate. We will be working towards holding that meeting within sixty days after the first transfers are registered. The Sectional Title Register was opened, so La Caribe is officially up and running. If any buyers are interested in serving on the Body Corporate, please let Gabri Viljoen know on gabri@ps127.co.za.

Snagging

It is common in new developments that certain items will require rectification after occupation. We call this snagging. We urge you to carefully go through your new apartments and draw up a list of snag items which we can speedily rectify for you, and which will avoid unnecessary discomfort to yourselves once you have taken occupation.

Handover Folios

We will be presenting each new owner with a handover folio for their unit. This folio will contain all the necessary information, warranties, guarantees and useful phone numbers to make life in your new unit as uncomplicated as possible.

We thank you for your patience and support over the last few months. We as developers are committed to making your new investment a pleasure to live in and pleasing to your eye. The development is coming together in leaps and bounds, and we anticipate that in the next 8 months it will all be complete. We would urge you to physically visit the site to see this for yourself. You can also visit our web site www.lacaribe.co.za to see where we are in the construction phase. Naturally, those that have occupation by December may have to put up with the Block G construction site, but we intend to make that a minimal distraction to your lifestyle and views.

There will be no construction on Block G during the December builders’ holidays (mid December to 5 January 2009), and we will be putting up netting around the construction site. Access to the construction site will be prohibited during that time for obvious reasons, and we request that you be mindful of children around the construction site.

Our contact details

Should you have any queries with regard to the La Caribe development you are more than welcome to contact any of the following:

| Name | Company | Relationship | Position | Contact |
| --- | --- | --- | --- | --- |
| Gabri Viljoen | P S 127 | Developer | Financial/Marketing | 082 807 3450 gabri@ps127.co.za |
| Jan van der Merwe | P S 127 | Developer | Operations/Marketing | 076 777 0817 jan@ps127.co.za |
| James Hinton | C Max | Land owner and Phase 2 developer | CEO | 082 557 2512 james@ marinamartinique.co.za |

 www.lacaribe.co.za